## Installation(1)
This block of testing presents TC related to the installation the application
Mobile device - OnePlus 11 5G Model - CPH2449 OS - OxygenOS 14.0/Android 14/CPH2449_14.0.0.501(EX01)
TEST CASE ID | 171 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Downloading the application | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Check if the application can be downloaded from the Play Store (Spaces by Wix)
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | Searching application by the name in the Play Store | "Spaces by Wix" is visible, free and could be download | PASS
2 | Download the application on the phone | Application is successfully download without errors and charges | PASS
TEST CASE ID | 172 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Launching the application | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Check if the application can be opened on the phone without errors with enabled Internet
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | Find and open on the main phone menu the application "Spaces by Wix" | Application opens on the main menu with authorization form | PASS
TEST CASE ID | 173 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Launching the application | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Check if the application can be opened on the phone with disabled Internet
PRECONDITIONS | The User does not have an Internet connection
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | Find and open on the main phone menu the application "Spaces by Wix" | Application opens on the main menu with authorization form, but on the footer User could see notification "No internet. Some features may be unavailable." | PASS
TEST CASE ID | 174 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Deleting the application | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Check if the User can successfully delete the application
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | On the main phone menu find the application and choose option to delete | Application is correctly deleted from the phone and no data has left | PASS

## Authorization and Registration(
This block of testing presents TC related to the authorization in the application
Mobile device - OnePlus 11 5G Model - CPH2449 OS - OxygenOS 14.0/Android 14/CPH2449_14.0.0.501(EX01)
TEST CASE ID | 175 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Authentication in the application | DATE TESTED | 2024-03-09
TEST CASE DESCRIPTION | Check if the User can authorize in the application (Google account with invitation link)
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | In the authorization form choose "Log in with Google account" | The application offers different options for Users to choose a possible account | PASS
2 | Select the appropriate profile (where User has invitation link) and entry to the application | The application login was successful and User could interact with the application SKYBOT | PASS
TEST CASE ID | 176 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Authentication in the application | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Check if the User can authorize in the application (using Facebook)
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | In the authorization form choose "Log in with Facebook account" | The application asks for permission to choose an account for further actions | PASS
2 | Select the profile and entry to the application | The application login was successful but the User without special link didn't see the SKYBOT application to interact with | PASS
TEST CASE ID | 177 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Authentication in the application | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Check if the User can authorize in the application (using phone number)
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | In the authorization form choose "Log in with phone number" | The application asks to fill out all necessary lines and then Log in | SKIPPED (the current functionality has not yet been implemented)
TEST CASE ID | 178 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Authentication in the application | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Check if the User can authorize in the application (using email with invite link on it)
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | In the authorization form choose "Log in with email" | The application asks to fill out special form | PASS
2 | User type correct email and click "Continue" | After application accept the email it will ask to type password | PASS
3 | User write correct password and click "Log In" | Application shows to User main page with relevant sites | PASS
TEST CASE ID | 179 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Log out of the application | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Check if the User can successfully log out of the application
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | On the main menu screen, in the right bottom corner click on the icon "My profile" | The User see all possible options to interact with profile. | PASS
2 | Scroll down to the option "Log out" and click it | The User is successfully log out from the application and transfered to the authorization form | PASS

## Main functions(3)
This block of testing presents TC related to the main functions available in the application
Mobile device - OnePlus 11 5G Model - CPH2449 OS - OxygenOS 14.0/Android 14/CPH2449_14.0.0.501(EX01)
TEST CASE ID | 180 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | General Info Panel | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Verifying basic actions which located in the "General Info Panel"
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the main screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | Click on the button "General info" | User proceeds to another screen where is located all information about SKYBOT company (contacts, location) | PASS
2 | Click on the line with phone number | User is procced to screen with call elements, where he/she could connect with company by phone number | PASS
3 | Click on the link of the main web page of the SKYBOT | User is transferred to the main web page with scooters | FAIL | BUG => Outdated version of the site https://prometheus-qa.atlassian.net/browse/SMA-117
TEST CASE ID | 181 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | General Info Panel | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Verify option Invite members which located in the "General Info Panel"
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the main screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | Click on the button "General info" | User proceeds to another screen where is located all information about SKYBOT company (contacts, location) | PASS
2 | Scroll down to the section "Invite Members" and click on it | Opens a new tab where User could choose one of the possible options to invite members | PASS
3 | Choose "Email Wix Contacts" | Opens a new screen with form, where User could invite all Wix contacts | PASS
4 | Choose "Send an SMS" | Opens a message app on the phone, where User could send the link by SMS | PASS
5 | Choose "Copy link" | Phone shows notification "Link is copied" | PASS
6 | Choose "GMail" | User proceeds to another app "GMail" where he/she could sent email with invitation link | PASS
TEST CASE ID | 182 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | SHOP screen | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Verify option to filter products
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the main screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | Click on the special icon responsible for filtering products | User see 2 lines - Category and In stock | PASS
2 | Click on the "Category" | User see 4 categories available - "Spare parts for scooters", "Електросамокати", "Ride safely" and "All products" | FAIL | One position - in Ukrainian language
3 | Click on the category "Електросамокати" | User will see products just in the category elecrtic scooters | FAIL | Not all items match the declared filter
4 | Click on the category "Ride safely" | User will see products just in the category "Ride safely" (protection items) | FAIL | Not all items match the declared filter
5 | Click on the category "Spare parts for scooters" | User will see products just in the category "Spare parts" | FAIL | Not all items match the declared filter
6 | Enable option "In stock" | App will filter all items and shows only items with mark "In Stock" | FAIL | Elements are presented out of the order
7 | Click on the category "All products" | App will show all items | FAIL | BUG => Filter function isn't working https://prometheus-qa.atlassian.net/browse/SMA-118
8 | Click on the filter option by "Brand" | User will see list with different brands and will have option to choose | SKIPPED (the current functionality has not yet been implemented)
9 | Click on the filter option by "Price" | For User will be presented different price options to choose | SKIPPED (the current functionality has not yet been implemented)
10 | Click on the filter option by "Rating" | User could filter all items by the raiting which is visible on each item | SKIPPED (the current functionality has not yet been implemented)
TEST CASE ID | 183 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | SCHEDULE screen | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Verify tab with Schedule
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the main screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | Click on the tab "Schedule" | The user will see the schedule of necessary service inspections or the date when their insurance expires | BLOCKED | https://drive.google.com/file/d/13uTyI3_UUxKqQMPvMVodzbySeWMAmfuh/view?usp=sharing
2 | Click on the tab "Schedule" and check if application displays correct day of the year | The app will highlight today's calendar day | PASS
TEST CASE ID | 184 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | SERVICES screen | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Verify tab with Services
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the main screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | Click on the tab "Services" | The user will see propositions to reserve different kind of services (First ride, Scooters service and Scooters for rent) | BLOCKED | https://drive.google.com/file/d/14-752mEbVAx9CQBZKnO03vDn37tnqJFz/view?usp=sharing
TEST CASE ID | 185 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Videos screen | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Verify tab with Videos
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the main screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | Click on the tab "Videos" | The User will see tab with videos which presented in the app | PASS
2 | Click on the button "Play all" | New window will opens with all videos in the list | PASS
3 | Play first video "How to ride an Electric Scooter: Complete Guide & Tips" (added with v. 2.0) | The video plays without interruptions. All functions are available, also User can go to the YouTube page | PASS
4 | Play second video "Why americans have a love-hate relationships with e-scooters" (added with v. 2.0) | The video plays without interruptions. All functions are available, also User can go to the YouTube page | PASS
5 | Play third video "Repairing an Electric scooter after a car accident - ASMR restoration by Dr. Drei" (added with v. 2.0) | The video plays without interruptions. All functions are available, also User can go to the YouTube page | PASS
6 | Play fourth video "PET's new MOTORUN dual-motor e-scooter in action" | The video plays without interruptions. All functions are available, also User can go to the YouTube page | PASS
7 | Play fifth video "Razor's Next Gen E Scooter "C25" - Ride Razor" | The video plays without interruptions. All functions are available, also User can go to the YouTube page | PASS
8 | Play six video "Best Foldable Electric Scooter 2023 ¦ Top 10 Lightweight And Fastest foldable electric scooters" (added with v. 2.0) | The video plays without interruptions. All functions are available, also User can go to the YouTube page | PASS
9 | Play seventh video "Introducing the Protrek X-6 E-Scooter" (added with v. 2.0) | The video plays without interruptions. All functions are available, also User can go to the YouTube page | PASS
10 | Play eighth video "Fastest Farthest Biggest Baddest - Dualtron X Limited Review" (added with v. 2.0) | The video plays without interruptions. All functions are available, also User can go to the YouTube page | PASS
11 | Play ninth video "Top 5 Best Cheap Scooters 2023! - We Tested Them All!" (added with v. 2.0) | The video plays without interruptions. All functions are available, also User can go to the YouTube page | PASS
12 | Play tenth video "Segway Ninebot EKickScooter ZING C9 Review" (added with v. 2.0) | The video plays without interruptions. All functions are available, also User can go to the YouTube page | PASS
13 | Play eleventh video "Massive Fat Tire Electric Scooter! (Zoomer 2 Review))" (added with v. 2.0) | The video plays without interruptions. All functions are available, also User can go to the YouTube page | PASS
14 | Play twelfth video "Simple One Launched - India’s Longest Range Electric Scooter" (added with v. 2.0) | The video plays without interruptions. All functions are available, also User can go to the YouTube page | PASS
TEST CASE ID | 186 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Chat option | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Verify possibility to communicate by using the Chat option
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the main screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | Click on the tab "Chat " in the footer | In the new scrren opens a list with all User conversation | PASS
2 | Open conversation with Skybot and send "Hello" | User could receive response after some time | FAIL
3 | Open conversation with Members and send "Hello" | Users could communicate with each others in real time | PASS
TEST CASE ID | 187 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | GROUPS tab | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Verify possibility to join group "Група Skybot"
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the main screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | Click on the tab "Groups " in the main menu bar | In the new scren opens a list with all groups | PASS
2 | User click on the button "Join Group" | Application presents a pricing plan for User (10 lessons to become a pro rider) | PASS
3 | User choose option and click "Select" | Application presents a new tab with summary | PASS
4 | After re-cheking all information, User click "Checkout" | User will be transfered to the new tab with possibilities to change when plan will start | PASS
5 | User click on the button "Send message" | BLOCKED |  | Send message option (checkout).jpg
TEST CASE ID | 188 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | GROUPS tab | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Verify possibility to create group
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the main screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | Click on the tab "Groups " in the main menu bar | In the new scren opens a list with all groups | PASS
2 | Click on the option "Group list" | Users will see all approved groups | PASS
3 | Click on the option "Create Group" | Application presents a variety of different templates | PASS
4 | Choose "Fan Club" | User could edit name of the group, pick main photo and choose visibility (private or public) | PASS
5 | Click "Done" | User will wait until Admin accept the group | PASS
TEST CASE ID | 189 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | MEMBERS tab | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Verify possibility to see all members of the group
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the main screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | Click on the tab "Members" in the main menu bar | In the new screen opens a list with all members | PASS
2 | User could interact with list | List is active and Users could interact with it (scroll, open profiles) | PASS
3 | Open profile of one of the Members | Opens a new tab with information about Member (photo, name and surname, followers and following) | PASS
4 | Click on the button "Message" | Opens tab with chat where members could communicate (F2F) | PASS
5 | Click on the button "Follow" | After choosing this option User could follow this profile | FAIL | [BUG] - Option to follow isn't work properlly https://prometheus-qa.atlassian.net/browse/SMA-120

## Cart and checkout options(4)
This block of testing presents TC related to the actions with cart and chechout process available in the application
Mobile device - OnePlus 11 5G Model - CPH2449 OS - OxygenOS 14.0/Android 14/CPH2449_14.0.0.501(EX01)
TEST CASE ID | 190 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Adding item to the cart | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Verify possibility to add products to the cart
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the main screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | In the SHOP menu pick one item (Skybot Nexus C25) and open it | User see screen with all information about this scooter | PASS
2 | Click on the button "Add to the cart" | User see notification "You added 1 item to the cart" and cart icon is changing and displays quantity of items in the cart | PASS
TEST CASE ID | 191 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Cart managing | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Verify functions of the cart with products
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User has been earlier added to the cart with several items (Skybot Nexus C25 x1 / Skybot Dualtron x1 / Skybot Extreamer x4) User is on the main screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | On the main screen User select cart icon and click on it | Cart opens and displays all elements which were selected (Skybot Nexus C25 x1 / Skybot Dualtron x1 / Skybot Extreamer x3) | PASS
2 | Click on the first item in the list (Skybot Nexus C25) and select "View product" | After selecting this option User will be transfered to the item page with all information | PASS
3 | Swipe to the side or press the back button | User will return to the Cart panel | PASS
4 | Click on the second item in the list (Skybot Dualtron) and select option "Change quantity" | Opens a new tab with quantity option and will shop up a numeric keypad | PASS
5 | Click 5 on the keypad, click checkmark and press button "Apply" | The quantity have been changed and also changed total price of the order | PASS
6 | Click on the third item in the cart (Skybot Extreamer x4) and select option "Remove from cart" | After selecting option "Remove" all items (4) will be deleting from the cart and will recalcute total price | PASS
7 | Press "Promo code" option | Opens a new screen with blank line for Promocode | PASS
8 | Type "SpringRide" and press Apply | After using the Promocode, User will recieve a 15$ discount | PASS
9 | Press "Note" to add additional notes for the order | Opens a new tab with blank line | PASS
10 | Write some text and press "Apply" | Note will be added to the order | PASS
11 | Click on three dots on the right top corner and then press option "Clear Cart" | All elements from the cart will be deleted | PASS
12 | In the empty cart click on the option "Go back to store" | The User will be transfered to the shop page | FAIL | [BUG] - Inactive link https://prometheus-qa.atlassian.net/browse/SMA-119
TEST CASE ID | 192 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Cart managing | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Check the correctness of the promotional code, using the example of a product that has already had a discount
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User has been earlier added to the cart with several items with discount (Rear brake pads x1 / Bluetooth speaker x1) User is on the main screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | On the main screen User select cart icon and click on it | Cart opens and displays all elements which were selected (Rear brake pads x1 / Bluetooth speaker x1) | PASS
2 | Press "Promo code" option | Opens a new screen with blank line for Promocode | PASS
3 | Type "SpringRide" and press Apply | After using the Promocode, User will recieve a 15$ discount for all order | PASS
TEST CASE ID | 193 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Cart managing | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Check the correct reaction of the application when a user enters an incorrect promo code
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User has been earlier added to the cart with several items with discount (Rear brake pads x1 / Bluetooth speaker x1) User is on the main screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | On the main screen User select cart icon and click on it | Cart opens and displays all elements which were selected (Rear brake pads x1 / Bluetooth speaker x1) | PASS
2 | Press "Promo code" option | Opens a new screen with blank line for Promocode | PASS
3 | Type "SprongRide" and press Apply | Application reacts correctly and User see notification "Promo code isn't valid" | PASS
TEST CASE ID | 194 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Checkout process | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Verify correctness of the chechout process with incorrect address
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User has been earlier added to the cart with several items (Skybot Nexus C25 x1 / Skybot Dualtron x3) User is on the main screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | On the main screen User select cart icon and click on it | Cart opens and displays all elements which were selected (Skybot Nexus C25 x1 / Skybot Dualtron x3) | PASS
2 | Press button "Checkout" | User proceed to the next steps which is related with checkout process | PASS
3 | User fills in fields with the wrong address (country - Poland) | Application react correctly and User see notification that it is "Unsupported Region" | PASS
TEST CASE ID | 195 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Checkout process | DATE TESTED | 2024-04-06
TEST CASE DESCRIPTION | Verify correctness of the chechout process with correct address
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User has been earlier added to the cart with several items (Skybot Nexus C25 x1 / Skybot Dualtron x5) User is on the main screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | On the main screen User select cart icon and click on it | Cart opens and displays all elements which were selected (Skybot Nexus C25 x1 / Skybot Dualtron x5) | PASS
2 | Press button "Checkout" | User proceed to the next steps which is related with checkout process | PASS
3 | User fills in fields with the correct address and personal information (country - USA) | Application react incorrectly and User see notification that it is "Unsupported Region" | FAIL | The company SKYBOT is from the USA (all orders must procced without any mistakes)

## Reflection(5)
This block of testing presents TC which is connected to all products details in the application
Mobile device - OnePlus 11 5G Model - CPH2449 OS - OxygenOS 14.0/Android 14/CPH2449_14.0.0.501(EX01)
TEST CASE ID | 196 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Комплекти захисного екіпірування | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Комплекти захисного екіпірування | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Text is in Ukrainian language Text is chaotic https://drive.google.com/file/d/19pDBSJEFxxmYnnNAzNTlDsR2LZqKKnCk/view?usp=sharing
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 197 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Brake disc for Skybot 12" | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Brake disc for Skybot 12" | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Not enough technical information about details
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 198 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Rear brake pads | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Rear brake pads | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size) Low quality photo
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 199 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Brake handle for CityCoco | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Brake handle for CityCoco | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size) Unsuitable product description text
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 200 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Rubber mat for Skybot | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Rubber mat for Skybot | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size) Not an eye-catching photo
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 201 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Plastic upper X7 | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Plastic upper X7 | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size) Not an eye-catching photo
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 202 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Premium Power on lock | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Premium Power on lock | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size) Not an eye-catching photo Text is in Ukrainian language
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 203 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Two-way signaling | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Two-way signaling | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Not an eye-catching photo
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 204 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Junctek KF140G | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Junctek KF140G | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size, where was made)
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 205 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Turn signal relay for 60v. | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Turn signal relay for 60v. | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Description of the product does not match the product name!!! Not an eye-catching photo Text is in Ukrainian language
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 206 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Turn signal relay for 60v. | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Turn signal relay for 60v. | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size) Not an eye-catching photo Duplicate name
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 207 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of LED headlight for Skybot electric scooters | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with LED headlight for Skybot electric scooters | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size) Not an eye-catching photo
2 | User wants to use function "Notify When Available", click it and type e-mail address | Application asks relevant e-mail for future contact. User see notification "You'll be notifies when it's back" | PASS
3 | User click again to receive e-mail about this item. User gives the same e-mail address | Application react correctly and pops-up a notification "You've already dubmitted a request for this item. You'll be notified as soon as it's back." | PASS
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 208 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Original wiring with connectors for Skybot | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Original wiring with connectors for Skybot | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size) Not an eye-catching photo
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 209 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Battery power cable | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Battery power cable | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size) Not an eye-catching photo
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 210 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Universal Accelerator handle | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Universal Accelerator handle | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size) Not an eye-catching photo
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 211 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Accelerator grip | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Accelerator grip | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Text is not structured
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 212 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Wheel disc front for CityCoco with a diameter of 8 inches | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Wheel disc front for CityCoco with a diameter of 8 inches | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size, where was made)
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 213 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of "Tractor" rubber for 8-inch wheels for Skybot electric scooters | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with "Tractor" rubber for 8-inch wheels for Skybot electric scooters | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size, where was made) Not enough photos
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 214 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Wheel for scooter | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Wheel for scooter | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size, where was made) Not enough photos
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 215 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Engine cover in 8" wheel rim | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Engine cover in 8" wheel rim | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size, where was made) Not enough photos
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 216 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Cover for the engine in the wheel disc 12" under the brake disc | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Cover for the engine in the wheel disc 12" under the brake disc | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size, where was made) Not enough photos
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 217 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of The original programmable sine controller Kelly KLS 7230ST | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with The original programmable sine controller Kelly KLS 7230ST | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size, where was made) Text is not structured Not enough photos
2 | User wants to use function "Notify When Available", click it and type e-mail address | Application asks relevant e-mail for future contact. User see notification "You'll be notifies when it's back" | PASS
3 | User click again to receive e-mail about this item. User gives the same e-mail address | Application react correctly and pops-up a notification "You've already dubmitted a request for this item. You'll be notified as soon as it's back." | PASS
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 218 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Vector controller for brushless electric motor | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Vector controller for brushless electric motor | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size, where was made) Text is not structured Not enough photos
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 219 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Charger for Li-Ion 20S batteries | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Charger for Li-Ion 20S batteries | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size, where was made) Not enough photos Text is in Ukrainian language
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 220 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Charger for Skybot with a 60V battery | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Charger for Skybot with a 60V battery | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size, where was made) Not enough photos Text is not structured
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 221 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Collectorless electric motor QSMOTOR QS120 70H 2000W V1 72V | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Collectorless electric motor QSMOTOR QS120 70H 2000W V1 72V | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Text is not structured Not enough photos
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 222 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of 8 inchesmotor wheel | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with 8 inchesmotor wheel | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Text is not structured Not enough photos
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 223 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Motor wheel QS MOTOR 12" 3000W | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Motor wheel QS MOTOR 12" 3000W | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Text is not structured Not enough photos
2 | User wants to use function "Notify When Available", click it and type e-mail address | Application asks relevant e-mail for future contact. User see notification "You'll be notifies when it's back" | PASS
3 | User click again to receive e-mail about this item. User gives the same e-mail address | Application react correctly and pops-up a notification "You've already dubmitted a request for this item. You'll be notified as soon as it's back." | PASS
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 224 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Акумулятор 77,7V 18Ah | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Акумулятор 77,7V 18Ah | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Name of the item is in Ukrainian language Text is not structured Not enough photos
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 225 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Rechargeable Li-Ion battery for Skybot Extreamer | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Rechargeable Li-Ion battery for Skybot Extreamer | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size, where was made) Text is not structured Not enough photos
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 226 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Bluetooth speaker | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Bluetooth speaker | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size, where was made) Not enough photos
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 227 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Helmet for eletric scooter | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Helmet for eletric scooter | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size, where was made) Not enough photos No option to pick different colors (based on the photos)
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 228 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Front laether bag | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Front laether bag | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size, where was made) Not enough photos
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 229 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Skybot Day-to-day | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Skybot Day-to-day | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | NO technical description Photos are repeated mirror image
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 230 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Skybot Extreamer | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Skybot Extreamer | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Too limited technical description and product characteristics (weight, size, where was made) Text is not structured Not enough photos
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 231 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Skybot Child Scooter | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Skybot Child Scooter | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Price isn't relevant Too limited technical description and product characteristics (weight, size, where was made) Text is not structured Description is in Ukrainian language
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 232 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Skubot RoverX | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Skubot RoverX | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Error in the name of the scooter brand Too limited technical description and product characteristics (weight, size, where was made) Text is not structured Description is in Ukrainian language
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 233 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Skybot Dualtron | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Skybot Dualtron | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | The description text does not match the product photo (description of the skateboard). Description is in Ukrainian language
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 234 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of SSkybot Dualtron | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with SSkybot Dualtron | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Photo of the item doesn't match to the description section!!
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 235 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Skybot Protrec City | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Skybot Protrec City | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Not enough photos
2 | User wants to use function "Notify When Available", click it and type e-mail address | Application asks relevant e-mail for future contact. User see notification "You'll be notifies when it's back" | PASS
3 | User click again to receive e-mail about this item. User gives the same e-mail address | Application react correctly and pops-up a notification "You've already dubmitted a request for this item. You'll be notified as soon as it's back." | PASS
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 236 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Skybot Foldable | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Skybot Foldable | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Not enough photos
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 237 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Skybot Nexus C25 | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Skybot Nexus C25 | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Not enough photos Part of the description is in Ukrainian language
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED
TEST CASE ID | 238 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Detailed description of Skybot Motorun PET | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Checking the correctness of the display of technical features, photos of the item
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the SHOP screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User opens new tab with Skybot Motorun PET | Technical features are presented in a structured way. The text looks clear and in line with the screen. The photos are clear and relevant to the subject matter. The price is relevant to the market and is displayed in dollars. | FAIL | Text is not structured Part of the description is in Ukrainian language
2 | User want to leave review for this product | In the bottom, User will see special section for reviews | SKIPPED

## Personal profile(6)
This section presents test cases related to the actions with User's personal profile
Mobile device - OnePlus 11 5G Model - CPH2449 OS - OxygenOS 14.0/Android 14/CPH2449_14.0.0.501(EX01)
TEST CASE ID | 239 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Personal profile | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Check the main functions connected with the "My Profile" tab
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the main screen
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | Click on the right top corner icon with 3 dots | User will see a small menu with different functions | PASS
2 | Click on the name or nickname of the profile owner | New tab will opens with personal information about User which is visible for all Members | PASS
3 | Click the button "Edit profile" | Opens a new window for editing the profile | PASS
TEST CASE ID | 240 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Personal profile | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Check if User could change the main photo of the profile
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the main screen Profile editor is opened
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User wants to change the main photo | User could choose one of the photo from the memory of the mobile device | FAIL | The application shows notification with information "Your storage is full"
TEST CASE ID | 241 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Personal profile | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Check if User could change the name and surname of the profile
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the main screen Profile editor is opened
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | User wants to change the name and surname (alphabetic characters) and click Save | The action is successful. Other members see the last one edition | PASS
2 | User wants to change the name and surname (digital characters) and click Save | The action is successful. Other members see the last one edition | PASS
TEST CASE ID | 242 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Personal profile | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Check if User could change "About me" section
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the main screen Profile editor is opened
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | Scroll down to the paragraph "About me" and click on the button "Edit" | Opens a new tab with elements to adding new text, photo | PASS
2 | Type text "Hello world", make it bold and locate it in the center. Click on the button "Publish" | All actions with text are successful and correct | PASS
3 | Add some photo to the "About me" section | User could choose from the own storage of the mobile device | FAIL | The application shows notification with information "Your storage is full"
TEST CASE ID | 243 | CREATED BY | Mariia Mielnikova
TEST CASE TITLE | Personal profile | DATE TESTED | 2024-04-07
TEST CASE DESCRIPTION | Check if User could change Privacy setting of the profile
PRECONDITIONS | The User has the Internet enabled and stable WiFi connection The application is turned on User is on the main screen Profile editor is opened
DEPENDENCIES:
STEPS | STEP DESCRIPTION | EXPECTED RESULT | STATUS
1 | Scroll down to the paragraph "Privacy settings" | User see switch for binary operations that are executed immediately after the switch state is changed. | PASS
2 | User wants to make profile Private and swith off the switcher | After confirming the action, saving information and updating the tab User see information with message "Your profile is set to private" | PASS
3 | User wants to make profile Public and swith on the switcher | After confirming the action, saving information and updating the tab User see information with message "Your profile is public" | PASS